Product backlog

| Priority | Task Description | Estimate (Days) | Status | Assigned Member(s) |
| --- | --- | --- | --- | --- |
| High | Analyse user stories & define functional requirements | 1 |  | Product Owner, Scrum Master |
| High | Define system architecture (role-based access control) | 1 |  | Information Architect, Backend Developer |
| High | Design database schema from ERD | 1 |  | Database Designer |
| High | Create USER authentication module (secure login) | 1 |  | Backend Developer |
| High | Implement role-based access control (Student/Tutor/Staff/Admin) | 1 |  | Backend Developer |
| High | Develop Student–Tutor Allocation module | 2 |  | Backend Developer, Database Designer |
| High | Develop Meeting Management module | 2 |  | Backend Developer |
| High | Implement Meeting Outcome Recording | 2 |  | Backend Developer |
| High | Develop Document Upload & Secure Storage module | 2 |  | Backend Developer |
| High | Implement Document Commenting feature | 2 |  | Backend Developer |
| High | Develop Internal Messaging System | 2 |  | Backend Developer |
| High | Develop Blog Post Management module | 2 |  | Backend Developer |
| Medium | Implement Blog Commenting feature | 1 |  | Backend Developer |
| Medium | Develop Meeting Recording Upload feature | 2 |  | Backend Developer |
| Medium | Develop Notification Email System | 2 |  | Backend Developer |
| Medium | Develop Student Dashboard UI | 2 |  | Frontend Developer |
| Medium | Develop Tutor Dashboard UI | 2 |  | Frontend Developer |
| Medium | Develop Staff Monitoring Dashboard UI | 2 |  | Frontend Developer |
| Medium | Implement Bulk Allocation Functionality | 2 |  | Backend Developer |
| Medium | Implement Allocation History Tracking | 1 |  | Database Designer |
| Medium | Develop Statistical Reporting module | 1 |  | Backend Developer |
| Medium | Develop Exception Reporting module | 1 |  | Backend Developer |
| Medium | Implement Activity Logging System | 2 |  | Backend Developer |
| Medium | Implement Responsive UI Design | 1 |  | Frontend Developer |
| Low | System Integration Testing | 1 |  | Tester |
| Low | Functional Testing (Messaging, Uploads, Meetings) | 1 |  | Tester |
| Low | Security Testing (Role-based permissions) | 1 |  | Tester |
| Low | Fix identified defects | 1 |  | Frontend Developer, Backend Developer |
| Low | Prepare System Documentation | 1 |  | Product Owner |
| Low | Prepare Technical Documentation | 1 |  | Information Architect |
| Low | Final Report Writing | 2 |  | Product Owner |
| Low | Final Presentation Preparation | 2 |  | Scrum Master |

Sprint

| Sprint | Focus |
| --- | --- |
| Sprint 1 | Planning + Architecture + Database |
| Sprint 2 | Core Security & Role System |
| Sprint 3 | Allocation & Meeting Core |
| Sprint 4 | Document & Messaging System |
| Sprint 5 | Blog + Recording + Notification |
| Sprint 6 | Dashboards + Reporting + Logging |
| Sprint 7 | Testing + Documentation + Presentation |

Sprint 1 Planning & Foundation

| Task | Days |
| --- | --- |
| Analyse user stories & define functional requirements | 1 |
| Define system architecture (RBAC) | 1 |
| Design database schema from ERD | 1 |
| Project environment setup | 1 |
| Database implementation | 2 |
| Sprint review & documentation update | 1 |

Total = 7 Days

Team:
Product Owner, Scrum Master, Information Architect, Database Designer

Sprint 2 Planning & Foundation

| Task | Days |
| --- | --- |
| Create USER authentication module | 1 |
| Implement role-based access control | 1 |
| Develop Activity Logging System | 2 |
| Develop Notification Email System | 2 |
| Security validation testing | 1 |

Total = 7 Days

Team:
Backend Developer, Tester

Sprint 3 Security & User Management

| Task | Days |
| --- | --- |
| Develop Student–Tutor Allocation module | 2 |
| Implement Bulk Allocation Functionality | 2 |
| Implement Allocation History Tracking | 1 |
| Develop Meeting Management module | 2 |

Total = 7 Days

Team:
Backend Developer, Database Designer

SPRINT 4 Meeting Completion + Documents

| Task | Days |
| --- | --- |
| Implement Meeting Outcome Recording | 2 |
| Develop Meeting Recording Upload feature | 2 |
| Develop Document Upload & Secure Storage | 2 |
| Implement Document Commenting feature | 1 |

Total = 7 Days

Team:
Backend Developer

SPRINT 5 Messaging & Blog System

| Task | Days |
| --- | --- |
| Develop Internal Messaging System | 2 |
| Develop Blog Post Management module | 2 |
| Implement Blog Commenting feature | 1 |
| Develop Student Dashboard UI | 1 |
| Develop Tutor Dashboard UI | 1 |

Total = 7 Days

Team:
Backend Developer, Frontend Developer

SPRINT 6 Reporting + UI Completion

| Task | Days |
| --- | --- |
| Develop Staff Monitoring Dashboard UI | 2 |
| Develop Statistical Reporting module | 1 |
| Develop Exception Reporting module | 1 |
| Implement Responsive UI Design | 1 |
| System Integration Testing | 1 |
| Functional Testing | 1 |

Total = 7 Days

Team:
Frontend Developer, Backend Developer, Tester

SPRINT 7 Final Testing + Documentation + Presentation

| Task | Days |
| --- | --- |
| Security Testing | 1 |
| Fix identified defects | 1 |
| Prepare System Documentation | 1 |
| Prepare Technical Documentation | 1 |
| Final Report Writing | 2 |
| Final Presentation Preparation | 1 |

Total = 7 Days

Team:
Tester, Product Owner, Scrum Master